APN Partner Deal Acceleration Program

PROJECT PLAN

POC – Amazon Quick for Customs Operations

Knowledge Base Setup  |  Declaration Review & HS Classification  |  Regulations Q&A & Compliance

Table of Contents

1  PROJECT OVERVIEW	6

1.1  Executive Summary	6

1.2  Project Sponsor(s) / Stakeholder(s) / Project Team (pending)	6

1.3  Project Success Criteria	6

1.4  Project Assumptions	7

1.5  Out of Scope	7

2  SCOPE OF WORK	8

2.1  Use Case 1: Amazon Quick Foundation & Knowledge Base Setup - 2 Weeks	8

2.2  Use Case 2: Automated Customs Declaration Review & HS Code Classification - 3 Weeks	8

2.3  Use Case 3: Intelligent Q&A for Customs Regulations & Compliance Reporting - 3 Weeks	8

3  SOLUTION ARCHITECTURE	8

3.1  Use Case 1: Foundation & Knowledge Base Architecture	8

3.2  Use Case 2: Declaration Review & HS Classification Architecture	9

3.3  Use Case 3: Q&A & Compliance Reporting Architecture	9

4  SUMMARY OF MILESTONES & DELIVERABLES	11

4.1  Use Case 1: Foundation & Knowledge Base - Milestones & Deliverables (2 Weeks)	11

4.2  Use Case 2: Declaration Review & HS Classification - Milestones & Deliverables (3 Weeks)	11

4.3  Use Case 3: Q&A & Compliance Reporting - Milestones & Deliverables (3 Weeks)	11

4.4  Expected AWS Cost Breakdown by Services (pending)	11

5  RESOURCES & COST ESTIMATES(pending)	13

Partner Technical Team	13

Resources & Cost Estimate — All Use Cases (8 Weeks)	13

6  PATH TO PRODUCTION	14

6.1  Use Case 1: Foundation & Knowledge Base - Path to Production	14

6.2  Use Case 2: Declaration Review & HS Classification - Path to Production	14

6.3  Use Case 3: Q&A & Compliance Reporting - Path to Production	14

# 1  PROJECT OVERVIEW

## 1.1  Executive Summary

The Vietnam General Department of Customs (GDVC), the national customs authority under the Ministry of Finance, manages all import-export activities across Vietnam's borders. With rapidly growing trade volumes and increasing complexity of international regulations, customs officers face significant operational workload in areas such as declaration review, HS code classification, regulatory Q&A, and compliance reporting - tasks that are repetitive, time-consuming, and dependent on deep domain expertise.

To address this, GDVC is engaging TechX, an AWS Premier Tier Services Partner with proven expertise in GenAI and enterprise digital transformation. TechX will deploy Amazon Quick - an intelligent AI work companion purpose-built for enterprise and government workflows - to automate key customs operations, reduce manual processing time, and establish a scalable foundation for AI-enabled customs services. Amazon Quick provides native capabilities for custom chat agents, knowledge bases, automated workflows, business intelligence, and deep research, all governed through centralized admin controls. The engagement runs on the Amazon Quick Enterprise subscription, deployed in a supported AWS Region that provides Amazon Quick's agentic capabilities. The specific Region is confirmed with GDVC and the AWS account team before deployment. Amazon Quick is a managed AWS service accessed over HTTPS; it inherits the AWS compliance programs applicable to the selected Region, and access is governed through IAM Identity Center together with Quick's role-based access and custom permissions profiles.

TechX proposes a three-phase GenAI SCA engagement covering the following use cases:

- Use Case 1 (2 weeks): Amazon Quick Foundation & Knowledge Base Setup - deploying the Amazon Quick workspace, building Spaces with all customs regulations, and establishing the agent framework for downstream use cases.

- Use Case 2 (3 weeks): Automated Customs Declaration Review & HS Code Classification - agents that review import/export declarations for completeness and accuracy, and assist with HS code classification based on goods descriptions.

- Use Case 3 (3 weeks): Intelligent Q&A for Customs Regulations & Compliance Reporting - a natural-language Q&A agent for customs regulations with legal citations, plus automated compliance report generation.

## 1.2  Project Sponsor(s) / Stakeholder(s) / Project Team (pending)

| Name | Title | Role | Email / Contact |
| --- | --- | --- | --- |
| Project Escalation Contacts |  |  |  |
| Ha Ngo | CEO | Project Director | ha.ngo@techxcorp.com |
| Project Stakeholders |  |  |  |
| Phong Bui | Director | Project Director | phong.bui@techxcorp.com |
| Thang Le | Client Success Manager | Engagement Manager | thang.le@techxcorp.com |
| Partner Project Team |  |  |  |
| Khoa Than | Solution Architect | Solution Architect | khoa.than@techxcorp.com |
| Duy Nguyen | AI Engineer | AI Engineer | duy.nguyen@techxcorp.com |
| Sang Nguyen | AI Engineer | AI Engineer | sang.nguyen@techxcorp.com |
| Nguyet Hoang | Project Manager | Project Manager | nguyet.hoang@techxcorp.com |
| Anh Bui | DevOps Engineer | DevOps Engineer | anh.bq@techxcorp.com |
| Anh Dang | Tester | Tester | anh.dang@techxcorp.com |

## 1.3  Project Success Criteria

Use Case 1: Amazon Quick Foundation & Knowledge Base Setup:

- Knowledge Base successfully indexes ≥95% of provided regulatory documents.

- Regulatory lookup agent answers correctly ≥85% on a pre-agreed 50-question test set.

- At least 2 agents published and usable by a second business team.

Use Case 2: Automated Customs Declaration Review & HS Code Classification:

- Declaration Review Agent detects ≥80% of common errors on a 100-declaration test set.

- HS Classification Agent proposes the correct HS code at the 8-digit level within the top-3 suggestions for ≥75% of items in a 200-item test set. Final classification authority remains with GDVC officers.

- Average agent processing time is measured as a performance indicator on the agreed test set after the deployment region is confirmed; it is not an acceptance gate.

Use Case 3: Intelligent Q&A & Compliance Reporting:

- Q&A Agent answers correctly ≥85% with correct source citations ≥90%.

- Report Agent generates ≥3 report types matching GDVC-specified formats.

- End-user satisfaction score ≥4/5 from a 10-officer pilot group.

## 1.4  Project Assumptions

- The POC is deployed in the nearest available Amazon Quick region to Vietnam. GDVC acknowledges that agent processing - including anonymized test data - may occur outside Vietnamese territory. GDVC is responsible for confirming compliance with applicable data protection regulations (including Nghị định 13/2023/NĐ-CP and the Law on Cybersecurity) prior to POC kick-off.

- GDVC's AWS account is provisioned with the Amazon Quick Enterprise subscription for the duration of the engagement. TechX confirms which roles require Enterprise vs. Professional licensing prior to Week 1.

- GDVC is responsible for flagging regulatory documents that have been superseded, amended, or repealed before ingestion. After go-live, GDVC owns the process of updating the knowledge base when regulations change.

- Amazon Quick is configured with external web search disabled for all agents handling regulatory queries, ensuring responses are grounded exclusively in GDVC-provided documents.

- GDVC provides sample declarations (import/export), anonymized test data, and pre-agreed test cases - including a set of declarations with official HS codes assigned by GDVC officers to serve as ground truth for UC2 accuracy measurement. GDVC assigns a Domain SME with classification authority for this purpose.

- GDVC provides compliance report templates and quality evaluation criteria.

- GDVC provides a complete set of regulatory documents in digital, text-based format.

- GDVC assigns technical and business contacts for requirements clarification and UAT sign-off.

- All data used for the POC is Non-Production (no sensitive business information).

## 1.5  Out of Scope

- Direct integration with VNACCS/VCIS or other operational systems (POC is standalone only).

- Full replacement of human officers - AI supports decision-making, does not replace it.

- Processing of live, production-grade, or classified declarations. All data used in the POC - including shadow-mode pilot data in Phases 5-6 - must be anonymized or sanitized by GDVC prior to ingestion. Any use of non-anonymized data requires a separate data governance agreement.

- Real-time continuous monitoring of declaration streams - scope is on-demand review.

- Any work not explicitly listed in the Scope of Work sections. Additional work requires mutual agreement.

- Custom-built components outside Amazon Quick's native capabilities: no custom model hosting, vector store, citation engine or confidence-scoring engine. All agent behaviour is delivered through Quick configuration.

# 2  SCOPE OF WORK

This engagement delivers three use cases over 8 weeks. It establishes an Amazon Quick workspace for GDVC, builds comprehensive Spaces with customs regulations, and deploys specialized AI agents for declaration review, HS classification, regulatory Q&A, and compliance reporting.

## 2.1  Use Case 1: Amazon Quick Foundation & Knowledge Base Setup - 2 Weeks

Establish the enterprise foundation that enables all downstream agents to access customs knowledge reliably. Scope includes:

- Amazon Quick workspace deployment with security configuration appropriate for government agencies: IAM Identity Center authentication, custom permissions profiles, KMS encryption on the source S3 bucket, and TLS in transit.

- Space construction: ingest and index Customs Law, Decrees, Circulars, import-export tariff schedules, HS code nomenclature and customs clearance procedures.

- Enterprise governance configuration - establish Amazon Quick admin controls: data segregation by Chi cục (sub-department) using IAM Identity Center groups with space-level sharing, custom permissions profiles restricting capabilities per role, and web search disabled on all regulatory agents.

- Customs agent standards: Define mandatory citation format (Decree number, Article, Clause), confidence-flagging rules for low-certainty outputs, and escalation language when the agent cannot resolve a query. These are business standards enforced via agent instructions, not custom-built tooling.

- Test case library: Co-develop with GDVC Domain SME a pre-agreed set of test cases for UC2 and UC3 (100 declarations, 200 goods items, 50 regulatory Q&A pairs), including ground-truth answers, to be used as the acceptance benchmark across all use cases.

- Cross-platform validation of account and agent accessibility (web, mobile app, browser extension; the desktop app is validated on a best-effort basis as a preview capability).

## 2.2  Use Case 2: Automated Customs Declaration Review & HS Code Classification - 3 Weeks

Deploy specialized Amazon Quick agents that automate customs declaration checking and HS code classification. Scope includes:

- Declaration Review Agent: Ingests import/export declarations, checks completeness and validity against regulations, detects common errors (HS code mismatch with goods description, missing permits, incorrect tax rates), and outputs structured recommendations with flagged risks.

- HS Classification Agent: Receives goods descriptions in Vietnamese or English, proposes appropriate HS codes with classification rationale based on the current tariff schedule.

- Integration with Space containing tariff schedules, prohibited/restricted goods lists, and rules of origin.

- Evidence capture: Review results, classification rationale, and self-declared certainty levels retained in a POC evidence Space, audited through CloudTrail and the Quick analytics dashboard.

- Both agents validated against pre-agreed test cases (100 declarations, 200 goods items) and published to the shared workspace with documentation.

## 2.3  Use Case 3: Intelligent Q&A for Customs Regulations & Compliance Reporting - 3 Weeks

Deploy agents that enable natural-language regulatory inquiry and automated report generation. Scope includes:

- Regulations Q&A Agent: Customs officers can ask natural-language questions about clearance procedures, applicable tax rates, specialized inspection requirements, and FTA/C/O rules, receiving answers with specific legal citations (Decree number, Article, Clause).

- Compliance Report Agent: Automatically aggregates data and generates periodic compliance reports (violation statistics, risk classification, trends) in document or spreadsheet format per GDVC templates.

- Multi-turn conversation support: Follow-up questions and deep-dive into specific scenarios.

- Feedback mechanism: Officers can flag incorrect answers for agent improvement.

- Both agents validated against pre-agreed test cases and published with documentation.

# 3  SOLUTION ARCHITECTURE

## 3.1  Use Case 1: Foundation & Knowledge Base Architecture

This use case establishes the core infrastructure that all downstream agents depend on. The architecture comprises five main components:

- Amazon Quick Workspace serves as the central platform for agent management, knowledge indexing, and user access control. Amazon Quick is a managed service hosted on AWS infrastructure. It reads the regulatory corpus from GDVC's S3 bucket through the Amazon Quick service role; the bucket must be in the same Region as the Quick account. Quick is not deployed inside GDVC's VPC.

- Amazon Quick's built-in AI engine handles all natural language understanding, reasoning, and generation for agents. Model selection and inference are managed by the Amazon Quick platform; usage is metered in agent hours (AI processing time measured in seconds) under the Enterprise subscription.

- Amazon S3 acts as the persistent storage layer for regulatory documents, tariff schedules, and all operational evidence generated by agents.

- Knowledge bases are indexed by the managed index Amazon Quick provisions in the account's home Region; index consumption is measured in GB of source-file storage. Spaces group knowledge bases and other resources and are assigned to agents, allowing them to retrieve relevant regulatory passages with high precision.

- The Agent Framework defines standardized agent templates including prompt engineering patterns, guardrails, error handling, and a test-case harness used to validate every agent before publishing.

## 3.2  Use Case 2: Declaration Review & HS Classification Architecture

This use case deploys two specialized agents, each following a distinct processing pipeline:

Declaration Review Agent

- The user uploads a customs declaration (import or export) to the agent.

- The agent extracts key fields (goods description, HS code, declared value, origin, permits) and cross-references them against the Space containing applicable regulations, tariff schedules, and restricted goods lists.

- The agent validates each field against the relevant rules and produces a structured report indicating pass/fail status per field, flagged risks, and specific recommendations for correction.

HS Classification Agent

- The user inputs a goods description in Vietnamese or English.

- The agent performs semantic matching against the HS nomenclature stored in the Space, then applies the Amazon Quick AI engine reasoning to determine the most appropriate classification.

- The agent outputs the top 3 HS code suggestions along with self-assessed certainty levels (High / Medium / Low) and a written rationale, as directed by agent instruction. These levels are qualitative model self-assessments, not system-generated scores.

Evidence and Audit

- All review results, classification outputs, certainty levels and timestamps are retained in the POC evidence space, audited through AWS CloudTrail and the Amazon Quick admin analytics dashboard. Archival to Amazon S3 is delivered through a configured AWS action connector where GDVC requires it.

## 3.3  Use Case 3: Q&A & Compliance Reporting Architecture

This use case provides two complementary capabilities:

Regulations Q&A Agent

- A customs officer or business user submits a question in Vietnamese natural language.

- The agent reformulates the query for optimal retrieval, then searches the Space using hybrid keyword and semantic matching to find the most relevant regulatory passages.

- The Amazon Quick AI engine generates a comprehensive answer grounded in the retrieved passages, including specific legal citations (Decree number, Article, Clause). The agent supports multi-turn conversations for follow-up questions.

Compliance Report Agent

- Triggered on-demand or on a scheduled basis, the agent aggregates operational data from evidence logs and activity records.

- It applies GDVC-provided report templates to generate formatted compliance reports (DOCX or XLSX) covering violation statistics, risk classifications, and trend analysis.

- Reports are delivered to designated recipients through connected applications, or saved to a shared space for retrieval. Delivery to Amazon S3 uses a configured AWS action connector.

Feedback and Continuous Improvement

- Officers can flag any incorrect Q&A response through a built-in feedback mechanism. Flagged items are queued for expert review. Once corrected, the Space is updated and the agent is revalidated against the affected test cases.

# 4  SUMMARY OF MILESTONES & DELIVERABLES

## 4.1  Use Case 1: Foundation & Knowledge Base - Milestones & Deliverables (2 Weeks)

| Week | Milestone | Deliverables | Acceptance Criteria |
| --- | --- | --- | --- |
| Week 1 | Workspace & Knowledge Base Setup | Amazon Quick workspace deployed; Space with ≥95% regulations indexed | Workspace accessible; search returns relevant results for sample queries |
| Week 2 | Agent Framework & Publishing | Agent Design Framework document; 2 published agents; test harness validated | Agents pass 50-question test with ≥85% accuracy |

## 4.2  Use Case 2: Declaration Review & HS Classification - Milestones & Deliverables (3 Weeks)

| Week | Milestone | Deliverables | Acceptance Criteria |
| --- | --- | --- | --- |
| Week 3 | Agent Development & Knowledge Integration | Declaration Review Agent v1 HS Classification Agent v1 tariff data indexed in the knowledge base | Agents execute on sample data without errors |
| Week 4 | Testing & Validation | Test execution against 100 declarations + 200 goods items; evidence retained in POC evidence Space (with CloudTrail audit trail) | ≥80% error detection ≥75% correct HS classification |
| Week 5 | Hardening & Publishing | Both agents published with documentation; performance tuning complete | Average processing time recorded as a performance indicator Published and usable by second team |

## 4.3  Use Case 3: Q&A & Compliance Reporting - Milestones & Deliverables (3 Weeks)

| Week | Milestone | Deliverables | Acceptance Criteria |
| --- | --- | --- | --- |
| Week 6 | Q&A Agent Development | Regulations Q&A Agent v1; multi-turn conversation; legal citations via agent instruction | Agent answers sample questions with correct legal citations |
| Week 7 | Report Agent & Validation | Compliance Report Agent v1; 3 report templates; test execution on 100 Q&A pairs | ≥85% accuracy; ≥90% correct citations; reports match GDVC format |
| Week 8 | Feedback Loop & Publishing | Feedback mechanism deployed; both agents published; pilot with 10 officers | Satisfaction score ≥4/5; agents published and operational |

## 4.4  Expected AWS Cost Breakdown by Services

The figures below represent the projected annual run-rate (ARR) for a production deployment of 450 customs officers on the Amazon Quick Enterprise tier. All figures must be re-derived against GDVC's confirmed user count before submission.

Assumption:

| Subscription plan | Number of users | Unit Price (USD) | Total Monthly |
| --- | --- | --- | --- |
| Amazon Quick - Enterprise | 450 | 40 | 18,000 |
| Total monthly ($) |  |  | 18,000 |

| Service | Description | Monthly (USD) | First 12 months (USD) | % of Total |
| --- | --- | --- | --- | --- |
| Amazon Quick – Enterprise subscriptions | Subscription | 18,000.00 | 216,000.00 | 98.3% |
| Amazon Quick – Infrastructure fee | Flat USD 250 per account per month | 250.00 | 3,000.00 | 1.4% |
| Amazon Quick – agent hours (overage) | Estimated 20h overage/month for Flows/Automate at scale × $3/h | 60.00 | 720.00 | 0.3% |
| Amazon Quick – index storage (overage) | Corpus ~80 GB production, pooled entitlement = 22,500 GB → no overage | 0.00 | 0.00 | 0.0 % |
| Amazon S3 (Standard) | ~50 GB regulatory corpus + evidence archive | 1.50 | 18.00 | <0.01 % |
| Total |  | 18,311.5 | 219,738 | 100.00% |

# 5  RESOURCES & COST ESTIMATES

## Partner Technical Team

- Solution Architect: Khoa Than

- AI Engineer 1: Duy Nguyen

- AI Engineer 2: Sang Nguyen

- Project Manager: Phuong Pham

- Tester: Anh Dang

- DevOps Engineer: Anh Bui

## Resources & Cost Estimate - All Use Cases (8 Weeks)

| Project Phase | PM (Phuong) | SA (Khoa) | AIE 1 (Duy) | AIE 2 (Sang) | Tester (Anh.D) | DevOps (Anh.B) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Preparation | 8 | 12 | 16 | 14 | 4 | 6 | 60 |
| Design | 8 | 18 | 20 | 16 | 4 | 6 | 72 |
| Development | 12 | 24 | 38 | 32 | 6 | 8 | 120 |
| Testing | 8 | 14 | 18 | 16 | 12 | 6 | 74 |
| Rollout | 4 | 9 | 8 | 7 | 4 | 4 | 36 |
| Total Hours | 40 | 77 | 100 | 85 | 30 | 30 | 362 |
| Rate (USD/hr) | $80 | $100 | $90 | $90 | $80 | $85 | — |
| Total Cost | $3,200 | $7,700 | $9,000 | $7,650 | $2,400 | $2,550 | $32,500 |

Cost Contribution Distribution between Partner, Customer, and AWS:

| Party | Contribution (USD) | % of Total |
| --- | --- | --- |
| Customer (GDVC) | $0 | 0% |
| Partner (TechX) | $7,500 | 23.1% |
| AWS | $25,000 | 76.9% |

# 6  PATH TO PRODUCTION

Each use case follows a structured path from POC delivery through production deployment. The goal is to validate the solution in a controlled environment before expanding to broader operations.

## 6.1  Use Case 1: Foundation & Knowledge Base - Path to Production

- TechX delivers the Amazon Quick workspace and Spaces during Weeks 1-2, followed by UAT sign-off by GDVC against the pre-agreed 50 questions test set.

- GDVC IT department conducts a security and compliance audit covering network access, data encryption, and IAM policies. Any findings are remediated before production promotion.

- The configuration is promoted to production by creating the production Space and knowledge bases and loading the complete regulation corpus.

- TechX provides a 2 weeks hypercare period to ensure workspace stability and knowledge base completeness.

- Admin training sessions, operational runbooks, and support transition documentation are delivered to GDVC staff at the end of hypercare.

## 6.2  Use Case 2: Declaration Review & HS Classification - Path to Production

- TechX delivers both agents during Weeks 3-5 with test results demonstrating achievement of success criteria (≥80% error detection, ≥75% HS accuracy). GDVC conducts UAT and signs off.

- A 4 weeks shadow-mode pilot is conducted at a selected customs office with approximately 50 officers. Agents process sanitised copies of real declarations in parallel with the manual workflow; outputs are compared but do not affect actual clearance decisions.

- At the end of the pilot, accuracy metrics are reviewed against production-readiness thresholds (≥85% error detection, ≥80% HS accuracy). If thresholds are not met, targeted improvements are made and the pilot is extended by 2 weeks.

- Upon passing the validation gate, agents are deployed to all target customs offices as a decision-support tool. Final clearance decisions remain with human officers.

- TechX provides 4 weeks of hypercare with weekly performance reviews. Monthly updates thereafter incorporate officer feedback and newly issued regulations.

## 6.3  Use Case 3: Q&A & Compliance Reporting - Path to Production

- TechX delivers both agents during Weeks 6-8 with validated test results (≥85% Q&A accuracy, ≥90% citation correctness, report format compliance). GDVC conducts UAT and signs off.

- A 4 weeks pilot is conducted with 20 customs officers and 10 registered import-export businesses. Usage patterns, answer quality, and satisfaction scores are tracked throughout.

- The pilot must achieve an end-user satisfaction score of ≥4/5 and maintain citation accuracy of ≥90% on live queries before proceeding to production.

- The Q&A Agent is published as a self-service tool for all customs staff and registered businesses. The Compliance Report Agent is integrated into the monthly reporting workflow with automatic generation and delivery.

- TechX provides 4 weeks of hypercare with the feedback mechanism fully operational. Quarterly regulation updates (new Decrees, Circulars, tariff changes) are ingested and agents are revalidated.